## Sheet1
Test case ID | Objective | Preconditions | Test data | Expected Result | Test completion date | Status | Tester | Comments
1.0.0 | Testing the display turns on upon start up | System is off | Supply power to the board | Display will turn on, temperature and humidity will be displayed | 2021-04-14 | Passed | Luke Nugent
1.0.1 | Testing the temperature and humidity are updating with change | System is on and on the main conditions page | Apply heat using a lighter to the sensor | The display will show an increased temperature and humidity reading | 2021-04-16 | Passed | Luke Nugent
1.1.0 | Testing access to the options menu | System is on and on the main conditions page | Press the * key | The options menu will be displayed | 2021-04-16 | Passed | Luke Nugent
1.1.1 | Testing the options menu naviagtion cursor | System is on and on the options menu | Press the # key | Each time the # key is pressed the cursor will move to the next option | 2021-04-17 | Passed | Luke Nugent
1.1.2 | Testing access to each option in the menu | System is on and on the options menu | Press the * key when the cursor is over each option | When the cursor is over an option and the * key is pressed the respective page will be displayed | 2021-04-18 | Passed | Luke Nugent
1.2.0 | Testing the input of valid limits in the temperature page | System is on and on the temperature page | Input a 2 digit integer for upper and lower limit where upper limit is greater than lower limit | Correct numbers will be displayed on screen and new limits will be updated | 2021-04-19 | Passed | Luke Nugent
1.2.1 | Testing the input of invalid limits in the temperature page | System is on and on the temperature page | Input a 2 digit integer for upper and lower limit where upper limit is less than lower limit | Correct numbers will be displayed on screen and new limits will not be updated | 2021-04-20 | Passed | Luke Nugent
1.2.2 | Testing the input of valid limits in the humidity page | System is on and on the humidity page | Input a 2 digit integer for upper and lower limit where upper limit is greater than lower limit | Correct numbers will be displayed on screen and new limits will be updated | 2021-04-21 | Passed | Luke Nugent
1.2.3 | Testing the input of invalid limits in the humidity page | System is on and on the humidity page | Input a 2 digit integer for upper and lower limit where upper limit is less than lower limit | Correct numbers will be displayed on screen and new limits will be not updated | 2021-04-22 | Passed | Luke Nugent
1.2.4 | Testing the confirmed reset | System is on and on the reset page | Select yes on the reset page | The limits will be reset to the initial system values | 2021-04-23 | Passed | Luke Nugent
1.2.5 | Testing the cancelled reset | System is on and on the reset page | Select no on the reset page | The limits will be not be reset to the initial system values | 2021-04-24 | Passed | Luke Nugent
1.3.0 | Testing the upper limit response for temperature | System is on and on the main conditions page | Raise the temperature around the sensor to 27 degrees celcius | The upper limit LED will turn on | 2021-04-25 | Passed | Luke Nugent
1.3.1 | Testing the lower limit respons for temperature | System is on and on the main conditions page | Set lower limit to be 24 degrees and lower the temperature around the sensor to 23 degrees celcius | The lower limit LED will turn on | 2021-04-26 | Passed | Luke Nugent
1.3.2 | Testing the upper limit respons for temperature | System is on and on the main conditions page | Raise the humidity around the sensor to 61 % celcius | The upper limit LED will turn on | 2021-04-27 | Passed | Luke Nugent
1.3.3 | Testing the lower limit respons for temperature | System is on and on the main conditions page | Set lower limit to be 55 % and lower the humidty around the sensor to 54 % | The lower limit LED will turn on | 2021-04-28 | Passed | Luke Nugent
1.3.4 | Test both limits for temperature and humidity | System is on and on the main conditions page | Keep temperature and humidity between the limits | Both LED's will be off | 2021-04-29 | Passed | Luke Nugent
2.0.0 | Ensure the feedback loops in the circuit are working. | System is placed in working environment. | Apply heat to a thermistor to cause upper limit to be reached. | The fan will be activated | 2021-02-15 | Passed | Jordan McCloy | Thermistor and arduino uno was used in intial circuit testing to ensure a feedback loop was occuring.
2.0.1 | Testing the fan powering off when lower limit is reached. | System is placed in working environment. | While fan is running place it close to the thermistor to apply cold air | The fan will be deactivated | 2021-02-15 | Passed | Jordan McCloy | Arduino uno was used to test the basic functions of prototype 1 by setting upper and lower limits for light levels and temperature to create a basic feedback circuit before building on it by using an ESP32 and the BME680 sensor.
2.1.0 | Testing the LDR (off state) in prototype 1 | System is placed in working environment. | Apply light to the LDR | The LED will remain off | 2021-02-15 | Passed | Jordan McCloy
2.1.1 | Testing the LDR (on state) in prototype 1 | System is placed in working environment. | Cover the LDR with a cloth | The LED will be activated | 2021-02-15 | Passed | Jordan McCloy
Note on A1: qubsys: A unique Identifier for thr Test case
Note on G1: qubsys: The status of the Test case i.e. is it pending, passed or failed