## Sheet1
Test case ID | Objective | Preconditions | Test data | Expected Result | Test completion date | Status | Tester | Comments
1.0.0 | Testing the display turns on upon start up | System is off | Supply power to the board | Display will turn on, temperature and humidity will be displayed | 2021-04-14 | Passed | Luke Nugent
1.0.1 | Testing the temperature and humidity are updating with change | System is on and on the main conditions page | Apply heat using a lighter to the sensor | The display will show an increased temperature and humidity reading | 2021-04-16 | Passed | Luke Nugent
1.1.0 | Testing access to the options menu | System is on and on the main conditions page | Press the * key | The options menu will be displayed | 2021-04-16 | Passed | Luke Nugent
1.1.1 | Testing the options menu naviagtion cursor | System is on and on the options menu | Press the # key | Each time the # key is pressed the cursor will move to the next option | 2021-04-17 | Passed | Luke Nugent
1.1.2 | Testing access to each option in the menu | System is on and on the options menu | Press the * key when the cursor is over each option | When the cursor is over an option and the * key is pressed the respective page will be displayed | 2021-04-18 | Passed | Luke Nugent
1.2.0 | Testing the input of valid limits in the temperature page | System is on and on the temperature page | Input a 2 digit integer for upper and lower limit where upper limit is greater than lower limit | Correct numbers will be displayed on screen and new limits will be updated | 2021-04-19 | Passed | Luke Nugent
1.2.1 | Testing the input of invalid limits in the temperature page | System is on and on the temperature page | Input a 2 digit integer for upper and lower limit where upper limit is less than lower limit | Correct numbers will be displayed on screen and new limits will not be updated | 2021-04-20 | Passed | Luke Nugent
1.2.2 | Testing the input of valid limits in the humidity page | System is on and on the humidity page | Input a 2 digit integer for upper and lower limit where upper limit is greater than lower limit | Correct numbers will be displayed on screen and new limits will be updated | 2021-04-21 | Passed | Luke Nugent
1.2.3 | Testing the input of invalid limits in the humidity page | System is on and on the humidity page | Input a 2 digit integer for upper and lower limit where upper limit is less than lower limit | Correct numbers will be displayed on screen and new limits will be not updated | 2021-04-22 | Passed | Luke Nugent
1.2.4 | Testing the confirmed reset | System is on and on the reset page | Select yes on the reset page | The limits will be reset to the initial system values | 2021-04-23 | Passed | Luke Nugent
1.2.5 | Testing the cancelled reset | System is on and on the reset page | Select no on the reset page | The limits will be not be reset to the initial system values | 2021-04-24 | Passed | Luke Nugent
1.3.0 | Testing the upper limit response for temperature | System is on and on the main conditions page | Raise the temperature around the sensor to 27 degrees celcius | The upper limit LED will turn on | 2021-04-25 | Passed | Luke Nugent
1.3.1 | Testing the lower limit respons for temperature | System is on and on the main conditions page | Set lower limit to be 24 degrees and lower the temperature around the sensor to 23 degrees celcius | The lower limit LED will turn on | 2021-04-26 | Passed | Luke Nugent
1.3.2 | Testing the upper limit respons for temperature | System is on and on the main conditions page | Raise the humidity around the sensor to 61 % celcius | The upper limit LED will turn on | 2021-04-27 | Passed | Luke Nugent
1.3.3 | Testing the lower limit respons for temperature | System is on and on the main conditions page | Set lower limit to be 55 % and lower the humidty around the sensor to 54 % | The lower limit LED will turn on | 2021-04-28 | Passed | Luke Nugent
1.3.4 | Test both limits for temperature and humidity | System is on and on the main conditions page | Keep temperature and humidity between the limits | Both LED's will be off | 2021-04-29 | Passed | Luke Nugent
2.0.0 | Ensure the feedback loops in the circuit are working. | System is placed in working environment. | Apply heat to a thermistor to cause upper limit to be reached. | The fan will be activated | 2021-02-15 | Passed | Jordan McCloy | Thermistor and arduino uno was used in intial circuit testing to ensure a feedback loop was occuring.
2.0.1 | Testing the fan powering off when lower limit is reached. | System is placed in working environment. | While fan is running place it close to the thermistor to apply cold air | The fan will be deactivated | 2021-02-15 | Passed | Jordan McCloy | Arduino uno was used to test the basic functions of prototype 1 by setting upper and lower limits for light levels and temperature to create a basic feedback circuit before building on it by using an ESP32 and the BME680 sensor.
2.1.0 | Testing the LDR (off state) in prototype 1 | System is placed in working environment. | Apply light to the LDR | The LED will remain off | 2021-02-15 | Passed | Jordan McCloy
2.1.1 | Testing the LDR (on state) in prototype 1 | System is placed in working environment. | Cover the LDR with a cloth | The LED will be activated | 2021-02-15 | Passed | Jordan McCloy
3.0.0 | Testing for power on separate dark-detecting circuit board for prototype 2 | System is off with no battery | Insert battery in to snap | LED should turn on when power is on and LDR has low light intensity | 2021-04-19 | Passed | Gareth Bryans
3.1.1 | Testing for sensitivity of LDR | Circuit is on, potentiometer at lowest resistance so LDR is most sensitive | Apply finger over LDR | LED should be on nearly all the time due to resistance being low | 2021-04-19 | Passed | Gareth Bryans
3.1.2 | Testing sensitivity of LDR | Circuit is on, potentiometer at highest resistance so LDR is least sensitive | Apply finger over LDR | LED should be off in light conditions and glowing dimly in dark conditions | 2021-04-19 | Failed | Gareth Bryans | LED still shone brightly as before on low resistance. Maximum resistance of potentiometer not high enough
3.1.3 | Repeat of 1.4.2, except with additional resistor in series with potentiometer to increase resistance | Circuit is on, potentiometer at highest resistance so LDR is least sensitive | Apply finger over LDR | LED should be off in light conditions and glowing dimly in dark conditions | 2021-04-19 | Passed | Gareth Bryans
4.1.1 | Testing that the ESP32 can connect to the local 2.4GHz Wi-Fi network | ESP32 is not currently connected to any networks | Upload the Wi-Fi connection code to the ESP32 and analyse the Arduino IDE console output | ESP32 will connect to the local network without any problems | 2021-04-20 | Passed | Sam Ross
4.1.2 | Testing that the ESP32 can connect to a 2.4GHz smartphone hotspot | ESP32 is not currently connected to any networks | Upload the Wi-Fi connection code to the ESP32 and analyse the Arduino IDE console output | ESP32 will connect to the smartphone hotspot without any problems | 2021-04-20 | Failed | Sam Ross | The ESP32 could not connect to the either of the 2 smartphone hotspots that I tried due to type of Wi-Fi mode that is required for this web server
4.1.3 | Testing that the Bosch BME680 sensor can transfer its readings to the ESP32 via I^2C serial communications successfully | BME680 sensor connected up to the ESP32 for serial communications via I^2C | Upload the sensor test code to the ESP32 and analyse the Arduino IDE console output | The BME680 sensor will send its readings to the ESP32 successfully | 2021-04-20 | Passed | Sam Ross
4.1.4 | Testing that the system can be powered by a 5V power bank | The system is not currently connected to any power sources | Connect the power bank to the ESP32 and see if the system functions normally | ESP32 will not function any differently from when it was connected to a laptop | 2021-04-20 | Passed | Sam Ross
4.1.5 | Testing the maximum distance that the ESP32 can connect to the Wi-Fi network 30 meters away without the U.FL antenna | ESP32 is not currently connected to any networks | Stand 30 meters away from the router, upload the Wi-Fi connection code to the ESP32, and analyse the console output | ESP32 will not be able to connect to the local network | 2021-04-20 | Passed | Sam Ross
4.1.6 | Testing the maximum distance that the ESP32 can connect to the Wi-Fi network 30 meters away with the U.FL antenna | ESP32 is not currently connected to any networks | Connect the antenna and stand 30 meters away from the router, upload the Wi-Fi connection code to the ESP32, and analyse the console output | ESP32 will be able to connect to the local network | 2021-04-20 | Passed | Sam Ross
4.1.7 | Testing that the local web server is able to connect to the local network and run the web server code successfully | The system is currently idle | Upload the local web server code to the ESP32 and analyse the Arduino IDE console output | The system will show in the console that it is hosting the web server successfully | 2021-04-20 | Passed | Sam Ross | The Arduino IDE console shows that the web server is running successfully and it prints the IP address for accessing the server.
4.1.8 | Testing that a device connected to the same Wi-Fi network as the ESP32 can access the web server at the specified IP address and can load the web page | The system is currently idle | Upload the local web server code to the ESP32. Connect a device to the same network that the system is connected to and try to access the web server by trying to load the specified IP address on the device | The device will be able to load the web page successfully | 2021-04-20 | Failed | Sam Ross | The ESP32 reboots every time the user device tries to access the web page due to an error. There turned out to be a bug where the ESP32 could not host websites when using the % symbol for specifying device widths for the web page.
4.1.8 (Retry) | Testing that a device connected to the same Wi-Fi network as the ESP32 can access the web server at the specified IP address and can load the web page | The system is currently idle | Upload the new local web server code to the ESP32.. Connect a device to the same network that the system is connected to and try to access the web server by trying to load the specified IP address on the device | The device will be able to load the web page by accessing the specified IP address in the browser | 2021-04-20 | Passed | Sam Ross | The page now loads successfully on the device
4.1.9 | Testing that the BME680 readings that are updated every 30 seconds on the web page are the same as the readings being outputted into the IDE console | The system is currently idle | Upload the local web server code to the ESP32 and compare the readings on the web page to the Arduino IDE console | There should be virtually no difference between the readings in the console and on the website | 2021-04-20 | Passed | Sam Ross
Note on A1: qubsys: A unique Identifier for thr Test case
Note on G1: qubsys: The status of the Test case i.e. is it pending, passed or failed